## Tabelle1
Screen | Testing person | Testing time | Results | Result and Comments
New User | Balazsy Istvan | 2012-06-12 | PASSED | OK
Active Directory Import | Balazsy Istvan | 2012-06-12 | FAILED | It crashes with unhandled exception. (I wasn't logged in with domain user.)
Edit | Balazsy Istvan | 2012-06-12 | PASSED | Works, but the password input fields should be removed. They are not necessary on this screen.
Delete | Balazsy Istvan | 2012-06-12 | PASSED | OK
Rights -> Read | Balazsy Istvan | 2012-06-12 | FAILED | With only read access the user can create report and company and Only the can import reconciliation data, but the application crashes with AccessDenied exception. With only read access the “New” button and all form elements should be disabled on each screen. For example: Companies->Algemein->Country tab
Rights -> Write | Balazsy Istvan | 2012-06-12 | FAILED | Without write access the user can import companies.
Rights -> Export | Balazsy Istvan | 2012-06-13 | FAILED | Without export right the user can export reconciliation values.
Rights -> Send |  |  | NOT TESTED
Effective rights | Balazsy Istvan | 2012-06-13 | PASSED | OK
Roles | Balazsy Istvan | 2012-06-13 | PASSED | OK